## Preamble
NES 3578 PROPERTY DEVELOPMENT APPROVALS ADHERENCE CHECKLISTS
This checklist does not replace the Property Development Guidelines. The Property Development Guidelines take precedent over the checklist. This checklist is used by the Property Development Committee to support adherence to the PDG and owners as they develop their various building & landscaping projects.
The development process may take years depending on the Owner's timelines but the actual construction process shall be no more than 365 days from the start of excavation to the building completion. Landscaping shall be given an additional time as per the Property Development Guidelines and NES 3578 Bylaws.
Site visits on the most part will be scheduled with the owner, however periodic site visits may occur without scheduling as committee/ strata council members schedules may warrant.
The committee members and strata council members are supportive of the PDG's and are not here to police the guidelines but help guide Owners adherence to the agreed upon process. The process can be reviewed updated or changed through the involvement and agreement with Strata council, the PDG's committee and the Owners.

## Project Particulars
Owner Details
Lot#:
Owner Name:
Email:
Mobile:
Phone:
Mailing Address:
Architect Details
Architect Name:
Company Name:
Email:
Mobile:
Phone:
Contractor Details
Main Contact Name:
Company Name:
Email:
Mobile:
Phone:
Project Key Dates
Application for development date received:
Date of Excavation:
Expected Completion Date of project:
Expected Completion Date of Landscaping
Site Visits
Date & Reason for site visit:

## Phase 1 - Project Start
Section | Requirements | Adhere | Variance Requested | Variance Status | Comments
| PHASE 1 – Project Start | Yes / no | Describe | A - Accepted.
R - Rejected.
M – Modified.
4 | Submittal Requirements
4.02 | · Please submit materials appropriately detailed according to the phase of design.
· Drawings and sketches may be submitted in a scale of ¼ inch to 1 foot in accordance with RDCK preferred requirements or the metric equivalent.
4.03 | Preliminary Design Documents Received:
· Legal Survey
· Photos of site
· Preliminary site plan
· Preliminary elevations
· Preliminary finishes (exterior)
· Drainage plan
· 3D Rendering
· Diagrammatic Site Analysis
5 | Site and Landscape Design Guidelines
5.01 | Building Envelop Zone (BEZ)
Located within setbacks & Slopes less than 30%
5.02 | Designated Building Envelope (BE) – Main building & Decks with in prescribed area.
· 5m Setbacks with adjacent lots maintained
· 4.5m setback with roadways maintained
· BE within 20% of lot or 450 sq m
· Neighbour building to building privacy objective met.
· LOT 6 – has variance of 4.5 m on all setbacks
5.03 | Natural Area (NA)
· In compliance to NA Parameters
5.04 | Topography & Steep Slopes
· Building relates to the existing terrain following the natural topography of the lot.
· Steep slopes (30%) shall not be cleared of vegetation.
5.05 | Driveways and Parking Areas
· Minimize impact to existing vegetation
· Minimize impact on natural grades
5.06 | Modifications to Common Property
· If so needs a Special Resolution with 75% pass.
5.07 | Damage to Common Property
· Does project require bonding due to potential damage?
5.08 | Views & Privacy
· Does the plan comply to community intent?
· Screening, deck placement etc.
5.09 | Landscaping (Preliminary design comply)
5.11 | Landscaping elements
· Retaining wall less than 1.5m
· Fencing within parameters
6 | Building Design Guidelines
6.01 | Building to Building Relationship consistent to The Vision of community (Privacy)
6.02 | Building Size
· Refer to 5.02
6.03 | Height within guideline parameters. Max 2 storeys with basement
6.04 | Exterior Materials
6.05 | Exterior Colours
6.06 | Roof Parameters
· Sloped/flat
· Solar panels
6.07 | Window Parameters
· Type /colour
· Placement (Restrict views of neighbour)
6.08 | Accessory Buildings >100 sq ft
· Materials and massing consistent with primary building.
· Guest House less than 500 sq ft
· Garage max 2 car plus hobby area
· Sheds under 100 sq ft must be concealed from view

## Phase 2 - Design
Section | Requirements | Adhere | Variance Requested | Variance Status | Comments
| PHASE 2 – Design | Yes / no | Describe | A - Accepted.
R - Rejected.
M – Modified.
4 | Submittal Requirements
4.02 | · Please submit materials appropriately detailed according to the phase of design.
· Drawings and sketches may be submitted in a scale of ¼ inch to 1 foot in accordance with RDCK preferred requirements or the metric equivalent.
4.04 | Detailed Building Design & Preliminary Landscape Documents Received:
· Detailed site plan includes all structures and elements
· Detailed exterior finishes; colour, type, location
· Exterior elevations
· 2 Building sections
· Drainage plan
· Utility approval documents from on-site utility provider
· 3D rendering
· Preliminary landscape designs
5 | Site and Landscape Design Guidelines
5.01 | Building Envelop Zone (BEZ)
Located within setbacks & Slopes less than 30%
5.02 | Designated Building Envelope (BE) – Main building & Decks with in prescribed area.
· 5m Setbacks with adjacent lots maintained
· 4.5m setback with roadways maintained
· BE within 20% of lot or 450 sq m
· Neighbour building to building privacy objective met.
· LOT 6 – has variance of 4.5 m on all setbacks
5.03 | Natural Area (NA)
· In compliance to NA Parameters
5.04 | Topography & Steep Slopes
· Building relates to the existing terrain following the natural topography of the lot.
· Steep slopes (30%) shall not be cleared of vegetation.
5.05 | Driveways and Parking Areas
· Minimize impact to existing vegetation
· Minimize impact on natural grades
5.06 | Modifications to Common Property
· If so needs a Special Resolution with 75% pass.
5.07 | Damage to Common Property
· Does project require bonding due to potential damage?
5.08 | Views & Privacy
· Does the plan comply to community intent?
· Screening, deck placement etc.
5.09 | Landscaping (Preliminary design comply)
5.11 | Landscaping elements
· Retaining wall less than 1.5m
· Fencing within parameters
6 | Building Design Guidelines
6.01 | Building to Building Relationship consistent to The Vision of community (Privacy)
6.02 | Building Size - Refer to 5.02
6.03 | Height within guideline parameters. Max 2 storeys with basement
6.04 | Exterior Materials
· Compliment native foliage, rocks and surroundings blend with natural area
· Fireproof material
6.05 | Exterior Colours
· Colours inspired by native foliage, rocks and surroundings blend with natural area
6.06 | Roof Parameters |  |  |  | Flat roof must have dark appearance
· Sloped or flat
· Solar panels
· Fireproof material
6.07 | Window Parameters
· Type /colour
· Placement (Restrict views of neighbour)
6.08 | Accessory Buildings >100 sq ft
· Materials and massing consistent with primary building.
· Guest House less than 500 sq ft
· Garage max 2 car plus hobby area (max 580 sq ft internally)
· Sheds under 100 sq ft must be concealed from view

## Phase 3 - Construction
Section | Requirements | Adhere | Variance Requested | Variance Status | Comments
| Phase 3 - Construction | Yes / no | Describe | A - Accepted.
R - Rejected.
M – Modified.
4 | Submittal Requirements
3.05 | RDCK Building Permit copy or posted on site
4.05 | A. Pre-Excavation Site Review:
· Markings for the planned building and excavation are property situated as compared to the detailed site plan
· Count of large trees (4 inches in diameter, measured 18 inches above native ground) outside the approved building envelope removed for construction purposes; mitigation of these trees will be included in the detailed landscape plan
· Documented record of site visit including the date and approval to proceed if compliant with NES 3578 approved Detailed Design and confirming the RDCK building permit is posted at the site.
· Documented variances that impact approval to proceed - the owner or representative will be advised in writing, of the requirement to rectify the variance before proceeding further.
· Photographs taken to document the progress.
4.05 | B. Post-Excavation Site Review
· Site visits conducted 3, 6 and 9 months after the Pre-Excavation site visit as point checks to ensure building construction is proceeding to the approved detailed building design.
· Documented record of site visits, including the date and approval to proceed if compliant with NES 3578 approved Detail Design
· Documented variances that impact approval to proceed - the owner or representative will be advised, in writing, of the requirement to rectify the variance before proceeding further
· Photographs taken to document the progress.
4.05 | C. Construction Completed Works Review
· Owner or representative to inform the Property Development Approvals Committee upon completing Building Works,
· Documented record of site visit including the date and approval of Building Completed Works, assuming the following are in accordance with the approved detailed building design
· Exterior Elevations,
· Exterior Finishes, Colors and Placement,
· Building Sections,
· Photographs taken to document final results.

## Phase 4 - Landscaping
Section | Requirements | Adhere | Variance Requested | Variance Status | Comments
| Phase 4 - Landscaping | Yes / no | Describe | A - Accepted.
R - Rejected.
M – Modified.
4 | Submittal Requirements
4.02 | · Please submit materials appropriately detailed according to the phase of design.
· Drawings and sketches may be submitted in a scale of ¼ inch to 1 foot in accordance with RDCK preferred requirements or the metric equivalent.
4.06 | A. Landscape Documents & requirements
· The document required is a Detailed Landscaping Plan showing: pathways, decks, retaining walls, fences and accessory structures (e.g. pergolas, fire pits, gazebos)
· Final grading 3 to 5 m from building exterior borders
· Mitigation of large trees
· No Evasive Plants, fruit trees, berry bushes and other foliage that are attractive to bears.
4.06 | B. Periodic Site Reviews/ Approvals
· 2 - site visits review according to plan
· Documented date of site visit with approvals to proceed
· Documented variances
· Photographs taken to document progress
5.03 | The Natural Area - of your lot is outside the NES 3578 approved BE and includes the lot setback areas to the property line.
· ‘No net loss’ of trees and vegetation.
· No tree removal without approval; approvals only granted for access roads, construction space, a parking area, site services and sanitary installation.
· Removal of dead or dangerous trees.
· Replacement of screening vegetation, if required.
· Trees and foliage maintained between homes.
· Report of trees and vegetation to be removed.
· Sensitively placed decks, planting, landscaping, retaining walls accented with natural stone native to the area and other garden improvements within the NA are allowed if these Improvements are in the spirit of the Vision.
5.04 | Topography and Steep slopes
· Steep slopes vegetation remaining
· Steep slopes vegetation replaced
5.09 | · Landscaping looks natural, avoids extensive grassy lawn, does not emphasize lot boundaries and symmetrical plantings, and connects the home to its site without great contrast to the existing character of the surrounding vegetation.
5.11 | Landscape Elements
· Retaining Walls - natural stone finish related to area.
· Retaining wall no greater that 1.5 m in height.
· Fences - Where concealed from view, fences may be made from other, unobtrusive materials.
· Fences - Where visible from neighbouring lots, common property or the public road are constructed of wood or stone and must be no greater than 2 meters high.